## Sheet1
WIMTACH Projects Jobsheet
| Project Name |  | Orbbit
| Student Number |  | 301115893
| Student Researcher Name |  | Dinh Tu Tran
| Contract Start date |  | Jan 10,2022
| Contract End Date |  | May 06,2022
| Student E-mail |  | dtran106@my.centennialcollege.ca
| Student Contact Number |  | 6478693210
| Supervisor's Name |  | Majura
| Week | Date | Activity | Start Time | End Time | Hours | Total hours per week
| 1 | 2022-01-10 | Login, Sign Up, Verify, Forgot password UI | 9:00 | 17:00 | 7 | 35
|  | 2022-01-11 | Setting Profile UI | 9:00 | 17:00 | 7
|  | 2022-01-12 | Landing Page UI | 9:00 | 17:00 | 7
|  | 2022-01-13 | New Audience UI | 9:00 | 17:00 | 7
|  | 2022-01-14 | New Offer UI | 9:00 | 17:00 | 7
| 2 | 2022-01-17 | New Advert UI | 9:00 | 17:00 | 7 | 35
|  | 2022-01-18 | Current Offer UI | 9:00 | 17:00 | 7
|  | 2022-01-19 | Current Advert UI | 9:00 | 17:00 | 7
|  | 2022-01-20 | Current Audience UI | 9:00 | 17:00 | 7
|  | 2022-01-21 | Profile setting UI | 9:00 | 17:00 | 7
| 3 | 2022-01-24 | Profile setting UI | 9:00 | 17:00 | 7 | 35
|  | 2022-01-25 | Pricing + Wallet UI | 9:00 | 17:00 | 7
|  | 2022-01-26 | Unit Test Onboarding, Pricing, Help and Support | 9:00 | 17:00 | 7
|  | 2022-01-27 | Unit Test Profile Settings, New Audience, Advert, Offer, Insights | 9:00 | 17:00 | 7
|  | 2022-01-28 | Unit Test Current Advert, Offer, Audience | 9:00 | 17:00 | 7
| 4 | 2022-01-31 | Unit Test Wallet, Previous Cred Purchase, Spending Actitivy | 9:00 | 17:00 | 7 | 35
|  | 2022-02-01 | Integration: Onboarding | 9:00 | 17:00 | 7
|  | 2022-02-02 | Integration: Onboarding | 9:00 | 17:00 | 7
|  | 2022-02-03 | Integration: Onboarding + Deploy front end to live URL | 9:00 | 17:00 | 7
|  | 2022-02-04 | Fix deployment issue on AWS | 9:00 | 17:00 | 7
5
6
7
8
9
10
11
12
13
13
Total
Note on D11: Meeting (internal or external and subject), analyzes (of what), study (of what), research (of what), etc